## Sheet1
Tasks	Person	Comp Date	Status
Fix Login Failed situation	T.M	6/6/2024	In progress
Create Sign Up page	D.M	9/6/2024	In progress
Fix Name - Welcome Page instead of Main	T.M	6/6/2024	In progress
Wrong Status Pop up for Login Page	T.M	6/6/2024	In progress
Create “Jobs” page			To be scheduled
Create “Messages” page			To be scheduled
Create "Notification" page			To be scheduled
Create "MyLinks" page			To be scheduled
Create "Settings" page			To be scheduled
Create "Account" page			To be scheduled
Create Main Page			To be scheduled
Create Sign In Page	T.M	6/6/2024	In progress
Create "Control Panel" page			To be scheduled
SSL/TLS requests for Log In			To be scheduled